## Gantt Chart
Software AT3 Gantt Chart Documentation
Week |  |  | Week 1 ¦ February 3rd | [6 empty] | Week 2 ¦ February 10th | [6 empty] | Week 3 ¦ February 17th | [6 empty] | Week 4 ¦ February 24th | [6 empty] | Week 5 ¦ March 3rd | [6 empty] | Week 6 ¦ March 10th | [6 empty] | Week 7 ¦ March 17th | [6 empty] | Week 8 ¦ March 24th | [6 empty] | Week 9 ¦ March 31st | [6 empty] | Week 10 ¦ April 7th | [6 empty] | Holidays Week 1 ¦ April 14th | [6 empty] | Holidays Week 2 ¦ April 21st
Dates |  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Days |  |  | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
Key: | Projected:
Actual:
Task | Start | End | bar: Week 1 ¦ February 3rd 3 Mon to Week 6 ¦ March 10th 16 Sun
Section 1: Identifying and Defining | bar: Week 1 ¦ February 3rd 3 Mon to Week 6 ¦ March 10th 16 Sun
Write Client Scenario | 2025-02-03 | 2025-02-04 | bar: Week 1 ¦ February 3rd 3 Mon to Week 1 ¦ February 3rd 4 Tues
Fill In Environmental Specifications Table | 2025-02-05 | 2025-02-09 | bar: Week 1 ¦ February 3rd 3 Mon to Week 1 ¦ February 3rd 6 Thurs
Create Objectives List | 2025-02-05 | 2025-02-07 | bar: Week 1 ¦ February 3rd 5 Wed to Week 1 ¦ February 3rd 9 Sun
Write Perfomance Criteria | 2025-02-09 | 2025-02-14 | bar: Week 1 ¦ February 3rd 9 Sun to Week 2 ¦ February 10th 14 Fri
Fill Out IPO Chart | 2025-02-10 | 2025-02-15 | bar: Week 2 ¦ February 10th 10 Mon to Week 2 ¦ February 10th 12 Wed
Create Gantt Chart | 2025-02-14 | 2025-02-14 | bar: Week 2 ¦ February 10th 14 Fri
Section 2: Research and Planning | bar: Week 1 ¦ February 3rd 3 Mon to Week 6 ¦ March 10th 16 Sun
Conduct Research and Write Up Findings | 2025-02-23 | 2025-02-24 | bar: Week 3 ¦ February 17th 19 Wed to Week 3 ¦ February 17th 21 Fri
Research
Create 3 Data Flow Diagrams | 2025-02-24 | 2025-02-26 | bar: Week 4 ¦ February 24th 24 Mon to Week 4 ¦ February 24th 26 Wed
DFD's
Develop Detailed Wireframe Diagrams | 2025-02-27 | 2025-02-28 | bar: Week 4 ¦ February 24th 27 Thurs to Week 4 ¦ February 24th 28 Fri
Wireframes
Create Storyboard | 2025-02-27 | 2025-02-27 | bar: Week 4 ¦ February 24th 27 Thurs to Week 4 ¦ February 24th 28 Fri
Strybrd
Write Five Pseudocode Algorithms | 2025-03-02 | 2025-03-19 | bar: Week 4 ¦ February 24th 1 Sat to Week 4 ¦ February 24th 2 Sun
Pseudocode
Section 3.1 Development | bar: Week 1 ¦ February 3rd 3 Mon to Week 6 ¦ March 10th 16 Sun
Implement Version Control Codebase | 2025-02-20 | 2025-02-20 | bar: Week 3 ¦ February 17th 20 Thurs to Week 3 ¦ February 17th 21 Fri
Create Logbook | 2025-02-04 | 2025-02-04 | bar: Week 1 ¦ February 3rd 4 Tues
Section 3.2 Functional Prototype
Build a user interface | 2025-03-31 | 2025-07-21 | bar: Week 9 ¦ March 31st 31 Mon to Holidays Week 2 ¦ April 21st 27 Sun
Implement Core Features | 2025-04-01 | 2025-07-21 | bar: Week 9 ¦ March 31st 1 Tues to Holidays Week 2 ¦ April 21st 27 Sun
Create Data Management Systems | 2025-04-01 | 2025-07-21
Produce Security Features for App | 2025-04-01 | 2025-07-21
Design Five Advanced Features | 2025-04-01 | 2025-07-21